## Slide 1: Process Improvement Project
Matt Maloney
MBC638:38406

## Slide 2: Process Improvement Project – Reducing Car Usage
Define: 4/6 | Measure: 4/6 – 5/5 | Analyze: 5/6 | Improve: 5/6 – 6/4 | Control: 6/4 –
Problem statement: I rely too heavily on my car for transportation despite living in a neighborhood not far from my office, grocery stores, restaurants, parks, a brewery, and my barbershop. I am able-bodied, have a bicycle, and there are sidewalks through most of the area. Business impact: Using the federal mileage rate, the cost to operate my vehicle over the course of the Measure phase was $158.28. Extrapolated across an entire year, this cost is $1,925.76. | Trips were taken either by foot or by car. Trips by car: Sample size: 30 days Sample mean: 9.1 miles/day Range: 48.6 miles Standard deviation: 11.4 miles Trips by foot: Sample size: 30 days Sample mean: 3.7 Range: 7.2 Standard deviation: 2.5 ------------------------------------------------- Given this data, here is the hypothesis test: Ho: 9.1 (u1) <= Mean daily car usage (u2) Ha: 9.1 (u1) > Mean daily car usage (u2) | Chi-square: 1.015 DF: 2 P-value: .602 Conclusion: There is not a demonstrable relationship between weather and mode of transportation. | While I initially assumed that weather had a large impact on the decision to walk, it is clear that distance and purpose of trip are more important variables. This led me to ask: How can I limit distance traveled? How can I increase my maximum non-car distance? How can I increase towing capacity without relying on the car? Before taking measurements during the improve phase, I tuned up my bicycle and a child carrier trailer. I have used this setup in the past for running errands but have gotten away from it. | Trips by car: Sample size: 30 days Sample mean: 1.2 miles/day Range: 11.8 miles/day Standard deviation: 3.2 miles/day All other trips: Sample size: 30 days Sample mean: 6.2 miles/day Range: 8.2 miles/day Standard deviation: 2 miles/day -------------------------------------------- Results of hypothesis test: z: 3.65 corresponding probability: .99987 p: 0
Team: Matt, Kate, and Alma
 | cloudy | rainy | sunny | total
car | 11 | 19 | 27 | 57
walk | 13 | 13 | 24 | 50
total | 24 | 32 | 51 | 107
Weather and walking not related!
Cluster of low mileage car trips and cluster of high mileage car trips. Do they have the same cause?
We must reject the null hypothesis!
SQL: 1.5
SQL: 2.6

## Slide 3: Define
My problem is relying too heavily on my car for transportation. I live in a neighborhood not far from my office, grocery stores, restaurants, parks, a brewery, and my barbershop. I am able-bodied, have a bicycle, and there are sidewalks through most of the area.
While transit by car is not extremely expensive (especially in my Prius), the costs are not zero, which leaves room for improvement. Additionally, time spent in a car is less useful than time spent walking or bicycling.
Business impact: Using the federal mileage rate, the cost to operate my vehicle over the course of the Measure phase was $158.28. Extrapolated across an entire year, this cost is $1,925.76.
Because this cost is not too high and the stakes are very low, I will consider my improvements effective if I can decrease average daily car mileage, regardless of the magnitude.
Map:
  Circle: my house
  Star: my office
  Triangle: local co-op
  Rectangle: shopping district with coffee roaster, barber, restaurants

## Slide 4: Measure
Data was collected by recording the mileage and time of each trip made during the month-long measurement phase. In addition to these continuous categories, discrete data was collected about the purpose of the trip, the weather, and the destination.
There were 107 observations over a 30-day period. If we take each day as a sample instead of each individual trip, my daily car usage had a standard deviation of 11.4 miles. At a 95% confidence variable, this leaves me with a potential error of about four miles. Given that this is not a high-stakes scenario, that is fine with me.
My measurements may be imprecise, as I only measure to the tenth of a mile. Additionally, although I have tried to be diligent about recording every single trip, there may be a few observations that I forgot to log.
SQL calculation:
  I will use any day in which I drive 5 miles or more as a defect
  In my initial sample, there were 15 days (out of 30) where this condition was met (50%)
  DPMO = 500,000
  SQL = 1.5
Descriptive statistics:
    Trips by car:
    Sample size: 30 days
    Sample mean: 9.1 miles/day
    Range: 48.6 miles
    Standard deviation: 11.4 miles
    Trips by foot:
    Sample size: 30 days
    Sample mean: 3.7
    Range: 7.2
    Standard deviation: 2.5

## Slide 5: Data stratification tree
Stratification factors
X Variables
Measurements
Distance traveled
(Output Y)
How far do I travel?
Is transportation chose dependent on weather?
Questions About Process
On what modes of transportation do I rely?
Does the nature of a trip dictate the mode of transportation chosen?
How much time do I spend in transit?
Purpose
Mode
Weather
Length of time
Minutes elapsed during trip
Weather at time of trip
Purpose of errand:
  Groceries
  Restaurants
  Work
  Etc.
Walking, driving, or biking

## Slide 6: Analyze
Chi-square test for independence:
Chi-square: 1.015
DF: 2
P-value: .602
Conclusion:
There is not a demonstrable relationship between weather and mode of transportation.
If there is no relationship between weather and mode of transportation, what factors are influencing my decision?
 | cloudy | rainy | sunny | total
car | 11 | 19 | 27 | 57
walk | 13 | 13 | 24 | 50
total | 24 | 32 | 51 | 107

## Slide 7: Analyze
Histograms for trips taken on foot and trips taken by car
Here we see that distance is more likely related to the ultimate mode of transportation
Additionally, there is a cluster of low mileage trips that were still taken by car
So what types of choices am I making as I am deciding on my mode of transportation?
on foot:
by car:

## Slide 8: Analyze
Here is a process map for the decision process
Low mileage trips taken by car typically involve the transport of objects (groceries, one trip to the vet) or trips to the brewery (very close, but in a light industrial neighborhood that is not walkable)
High mileage trips tend to be to get groceries at stores that are further away, for miscellaneous shopping needs, or to take Alma to the dog park
What changes can be made to my routine that might allow for less driving? Two solutions come to mind: convert all low mileage trips to non-driving and further limit high mileage trips.
  For the former, I tuned up my bicycle as an alternative to walking and driving. For the latter, I made a commitment to walk Alma around the neighborhood instead of going to the dog park and pledged to shop at the co-op instead of at far-off grocery stores.

## Slide 9: Improve
During the second month (30 days), I made 92 trips. Again looking at individual days instead of each trip as the unit by which to evaluate, the descriptive statistics are as follows:
    Trips by car:
    Sample size: 30 days
    Sample mean: 1.2 miles/day
    Range: 11.8 miles/day
    Standard deviation: 3.2 miles/day
    All other trips:
    Sample size: 30 days
    Sample mean: 6.2 miles/day
    Range: 8.2 miles/day
    Standard deviation: 2 miles/day

## Slide 10: Improve
Hypothesis test
My sample data is continuous, and I am comparing an initial data set to a secondary data set (two sample)
Based on my H0 and Ha statements, I will be using an upper/right-tail test
  Ho: 9.1 (u1) <= Mean daily car usage (u2)
  Ha: 9.1 (u1) > Mean daily car usage (u2)
x-bar1: 9.1
x-bar2: 1.2
s1: 11.4
s2: 3.2
n1: 30
n2: 30
alpha (from slide 4): .05
results:
  z: 3.65
  corresponding probability: .99987
  p: 0
We must reject the null hypothesis! The observed difference between the results of the two samples cannot be explained by chance alone. The changes made to the process have resulted in a statistically significant change!

## Slide 11: Improve
What did I learn about my process?
  Changing small habits can lead to a more active lifestyle and a less costly transportation plan
  I can meet nearly all of my needs in my neighborhood
  I definitely learned that I don’t get out much!
SQL calculation:
  I will use any day in which I drive 5 miles or more as a defect
  In my secondary sample, there were 4 days (out of 30) where this condition was met (13.33%)
  DPMO = 133,333
  SQL = ~ 2.6

## Slide 12: Control
How will you use this information to hold the gains of improvement?
  This project has raised my awareness of my own transportation habits. My bike is all tuned up and I have enjoyed shopping more frequently at our community co-operative market. While my car avoidance might not remain so extreme, I think I have made some lasting changes to my habits!